## Inc Matrix
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (10/25/18) | Iteration 3* (11/29/18)
UC 1 | Register | 1 | 1
UC 2 | Login | 1 | 1
UC 3 | Logout | 1 | 1
UC 4 | View Profile | 2 | 2
UC 5 | Update Profile | 2 | 2
UC 6 | Make Reservation | 2 | 1
UC 7 | Search Car | 3 | 1 | 2
UC 8 | Calculate Amount | 3 | 2 | 1
UC 9 | Confirm Rental | 2 | 1 | 1
UC 10 | View Reservations | 2 | 1 | 1
UC 11 | View Reservation Detail | 2 | 2
UC 12 | Cancel Reservation | 2 | 2
UC 13 | View Rentals | 2 | 2
UC 14 | View Rental Detail | 2 | 1 | 1
UC 15 | Delete Reservation | 2 | 1 | 1
UC 16 | View Users | 2 | 2
UC 17 | View User Detail | 2 | 2
UC 18 | Update User Profile | 2 | 2
UC 19 | Revoke Renter | 1 |  | 1
| Total Effort Estimated |  | 27 | 9
| Total Effort Available |  | 36 | 9
| Team Size | 6
* Sum of the effort of each column must not exceed the ability of the team. Sum of the efforts of each row must not be less than the required effort.